## Slide 1: MFC5J3 Development Information
August. 02. 2021
Chassis & Safety | Advanced Driver Assistance Systems

## Slide 2: Agenda
MFC5J3 Solution Overview
1
System Architecture
2
Project Development Plan
3
HW/SW development status
4
CEM Available Component
5
Problem to be solved
6

## Slide 3: MFC5J3 Solution Overview
MFC5J3 is a front viewing automotive monocular camera system
MFC5J3 configures ADAS functions and will particularly support the fulfillment of the CNCAP and Euro NCAP
Base on MFC5J3, 1R1V and 3R1V system is under development:
  1R1V – MFC5J3 + LRR ARS5xx
  3R1V – MFC5J3 + LRR ARS5xx + 2 x SRR5xx (front L/R)
Function bundles processed inside MFC5J3 are listed below:
ACC, AEB, TJA, LDW, LKA, LDP, RDP, TSA, HLA.

## Slide 4: MFC5J3 Solution Overview
  Subcomponent Communication Topology
  1R1V – MFC5J3 + LRR ARS5xx
  3R1V – MFC5J3 + LRR ARS5xx + 2 x SRR5xx (front L/R)
1R1V
3R1V

## Slide 5: MFC5J3 Solution Overview
  1R1V – MFC5J3 + LRR ARS5xx
Front Monocular Camera
1.7MP @ 30FPS
FOV 110°
ARS5xx
Private CAN
Public CAN
TC387

## Slide 6: MFC5J3 Technical Overview
Horizon J3
Perception
Aurix TC387
CEM
Driving
Function
Continental
Basic Software
Horizon
ACC
AEB
LCF
HLA
TSR
1R1V Solution

## Slide 7: MFC5J3 Project timing (1R1V)
2021
2022
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
PV
DV
B Sample
BSW Bug fix
PPAP
Pre DV
build
BSW dev.
Perception SW Development+bug fix
BSW development
A Sample
Components sourcing
Perception SW tuning+bug fix
Industrialization
Function development+bug fix
Performance tuning and bug fix
Perception SW Development
Function Development
CEM&DF
Full Function SW
08/02/2021
EMS
Production
Perception
SW final release
SOP
MFC5J3
PSW
1st SW Integration
BSW
HW
Full Function

## Slide 8: MFC5J3 1R1V HW development status
Schematic – Design on going by Conti
  Plan to release schematic mid Aug.
  Time duration: middle July to middle August.
PCB - on sourcing
  PCB design, simulation, manufacture vendor is on sourcing.
  Time plan: Gerber release at middle of September, time pressed.
Camera module - on sourcing
  Eight 8M optical modules from Foxcom have been received.

## Slide 9: MFC5J3 1R1V SW development status
TC387 EB Autosar stack purchase in process
  Questionnaire submitted, wait for quote.
  Consider use temporary Autosar stack for advanced development with G-Pulse.
Role & Response
  [TC387]Driving function by Conti: RTE interface first version complete.
  [J3]Fusion function by Conti: J3 development strategy under discussion with Horizon.
  [TC387]SPI Interface by G-Pulse: Interface under discussion with Horizon.
  [TC387]MTS by Conti: Strategy confirmed, to be implemented.

## Slide 10: MFC5J3 DF SW development Strategy
In order to accomplish the full function SW of 1R1V solution milestone in Q1 2022, it is decided to take CEM + ACC Gen4 as current longitudinal function architecture:
Function ECU
Gen4 ACC Functions
Radar ECU
Signal Processing
Environmental Model
Illumination and Preprocessing
Object Selection
Raw Data
F
Cluster List
Object Selection
Object List
40 Relevant Objects
Function ECU
Gen4 ACC Functions
MFC5J3
Signal Processing
CEM
Illumination and Preprocessing
Raw Data
F
Cluster List
Object List ??
22 Relevant Objects ??
Road/Lane info ??
F
- Fusion

## Slide 11: MFC5J3 CEM Component
Component | Available for ACC Gen4?
SEF Static Environment | No
EML Ego Motion & Localization | No
TPF Traffic Participants | Yes
RMF Road Modle | TBD
FSF Freespace | No
PCL Parking & Curb Lines | No
TCI Traffic Control Information | No
COH Coherence & Scene Detection | No

## Slide 12: COH Component Functionality

## Slide 13: Lane Assignment Sub-component Functionality
Lane Assignment
Determine which traffic participant (TP) is driving on which lane
Calculation depends heavily on the output of TPF and RMF components, and as well the camera data

## Slide 14: Problem to be solved
No. | Problem | Solution | Comment & Attachment
1 | Solution to be decide: TPF only -> Object List TPF + RMF + COH -> Object List w/ Lane Info | Have to use Solution a | 
2 | TPF only: If TPF output interface enough for ACC Gen4? |  | 
3 | TPF only: How to handle with missing interface? | Receive from Radar/Camera non fused output: e.g. Radar OD/LD, Camera Lane info | 
4 | TPF only: Does RMF module missing affect Cut-in Cut-out performance? | It is mandatory to have RMF module. Hard to ensure KPI without Lane & Road boundry information. | 
5 | Possibility of code management in Github? | Import ACC Gen4 algo into Github | 
6 |  |  | 
7 |  |  | 
8 |  |  | 

## Slide 15: Thank you
For your attention!